## Summary
Comms Log — Summary
Live counts — update automatically as you edit the Comms Log tab.
Metric | SMS | Email | Total
Total messages | 22 | 4 | 26
Sent to Lender | 7 | 1 | 8
Sent to Borrower | 15 | 2 | 17
Verified | 9 | 3 | 12
Needs attention | 5 | 1 | 6
Edit messaging on the "Log" tab. Placeholder keys live on the "Legend" tab.

## Test Scenarios
Test Scenarios — Transaction Comms QA
Live-data test plan for validating every SMS and email touchpoint. Scenarios ordered chronologically by where they diverge in the booking lifecycle. Priority: P0 = this sprint, P1 = next, P2 = edge / nice-to-have. AUTO_CANCEL_DRY_RUN=0 (live mode) and process.edn alias on v5 (24h lender expire) as of April 23 2026.
TEST ACCOUNTS
Role | First Name | Last Name | Email | Phone | Address
Borrower | <scenario> | BORROWER | amalia@shoponsherbet.com | 4152023068 | 1795 Chestnut St Apt 7, San Francisco, CA 94123
Lender | <scenario> | LENDER | amaliaebornstein@gmail.com | 5103977781 | 1745 Pacific Ave Apt 202, San Francisco, CA 94109
NAMING CONVENTION
Set the borrower's and lender's first names to the scenario label (e.g. 'IDEAL', 'IGNORED', 'DECLINED', 'UNSHIPPED', 'LATE', 'SUNDAY'). SMS copy interpolates ${borrowerFirstName} / ${lenderFirstName}, so the scenario name appears in every message — makes Twilio + SendGrid log inspection trivial.
SCENARIO OVERVIEW
# | Priority | Label | Phase | Description | Touchpoints exercised | Risk level | Status | Notes
1 | P0 | IDEAL | Full happy path | Borrower books, lender accepts within 60m, ships on time, borrower receives + returns on time, lender receives. | 1, 2a, 2c, 3, 4, 6, 7, 8, 10, 11 | LOW — no payment events | Eligible | Run this first as a smoke test of all Verified rows.
2 | P0 | IGNORED | Lender response window | Lender never accepts. Triggers 24h auto-expire (process.edn v5). | 1, 1a (60m), 1b (22h), Sharetribe expire email | LOW — borrower auto-refunded, no charges | Eligible | NEW: 1b-SMS at 22h is the 2-phase escalation final warning.
3 | P1 | DECLINED | Lender response window | Lender taps Decline within 60m. Borrower auto-refunded. | 1, 2b-SMS, 2b-Email | LOW | Eligible | Promotes 2b-SMS + 2b-Email to Verified on pass.
4 | P0 | UNSHIPPED | Outbound shipping window | Lender accepts but never ships. Triggers auto-cancel at bookingStart D + 12h scan-lag grace. | 1, 2a, 2c, 3, 3.1, 3.1b, 3.2, 3.2b | MEDIUM — real refund + label voids | Eligible | AUTO_CANCEL_DRY_RUN=0 is live; this is a real cancel test.
5 | P0 | LATE RETURN | Post-delivery return window | Borrower keeps item past return date. Day 1–6 overdue flow + $0.50 test charges (PR-4 dry-run). | 1, 2a, 2c, 3, 4, 6, 7, 8, 9.1–9.6, 9.6-Email, 9.7-Email, optionally 10/11 | HIGH — real Stripe charges | Eligible (env vars required) | Set LATE_FEE_CENTS_OVERRIDE=50 and OVERDUE_FEES_CHARGING_ENABLED=true in Render before running.
6 | P2 | SUNDAY EDGE | Calendar edge cases | 3 sub-cases: A=ship-by Sunday → Saturday adjust, B=Sunday end-date banner, C=Saturday reminder fire for Monday shipBy. | shipByDate adjust, Sunday banner UI, 3.1-SMS Saturday-fire | LOW — no payment events | Eligible | Run independently as 3 separate bookings.
SCENARIO 1 — IDEAL (baseline happy path) [P0]
Goal | Confirm the full baseline comms flow fires exactly once in correct order with no stragglers.
Setup | 1. Create borrower & lender test accounts (first names "IDEAL"). 2. Lender lists a cheap test item (e.g. $5/day, 3-day booking). 3. Borrower submits request. 4. Lender accepts within 60m (so 1a/1b nudges should NOT fire). 5. Lender ships on/before ship-by date. 6. Borrower receives, then ships return on time. 7. Lender receives.
Related PR / Feature | Baseline — not tied to a specific PR. Regression check for all Verified comms.
How to observe | Twilio console (filter by to-number), SendGrid activity feed (filter by recipient), Sharetribe Console → Transactions → latest tx → protectedData, Render logs filtered by scenario first-name "IDEAL".
Notes | AUTO_CANCEL_DRY_RUN=0 is live; if the lender accidentally misses the ship-by, this scenario will branch into Scenario 4 territory.
Expected comms (should FIRE)
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Pass? | Notes
1-SMS | 1 - New borrow request | SMS | Lender | Request created | Immediate on submit | Sherbrt 🍧: ... You have 24hrs to accept: [request_link].
1-Email | 1 - New borrow request | Email | Lender | Request created | Immediate on submit | Sharetribe template booking-new-request — date enforces 24h (delayed-transition.run-at).
2a-SMS | 2a - Request accepted | SMS | Borrower | Lender accepts | Immediate on accept transition | 🎉 Sherbrt 🍧: Your request for "[Item]" was accepted! ...
2a-Email | 2a - Request accepted | Email | Borrower | Lender accepts | Immediate on accept transition | Sharetribe template booking-accepted-request
2c-SMS | 2c - Return Label Provided | SMS | Borrower | Lender accepts (same accept transition) | Immediate on accept transition | 📦 Your return label is ready! Use this to ship back: [Label link]
3-SMS | 3 - Outbound label / QR created | SMS | Lender | Outbound shipping label or QR created | When label creation succeeds (~immediately after accept) | Sherbrt 🍧: Ship "[Item]" by [Ship-by Date]. Shipping label: [qr_or_label_link].
4-SMS | 4 - Item shipped (outbound) | SMS | Borrower | First "accepted" carrier scan (outbound) | On first scan | 🚚 Sherbrt 🍧: "[Item]" is on its way! Tracking info: [tracking_link].
6-SMS | 6 - Item delivered to borrower | SMS | Borrower | Delivered scan (outbound) | On first delivered scan | 🎁 Your Sherbrt borrow has arrived! ...
7-SMS | 7 - Borrower Return Reminder | SMS | Borrower | T-1 to return date AND no return scan | T-1 to [Return Date] (PT morning, gated by quiet-hours) | 📦 Sherbrt 🍧: It's almost return time! Use your QR/label to ship "[Item]" back tomorrow: [link].
8-SMS | 8 - Day-of-return reminder | SMS | Borrower | [Return Date] AND no return scan | Morning of [Return Date] | ⏰ Sherbrt 🍧: Today's the day for you to ship back "[Item]"! Late returns may incur $15/day fees. ...
10-SMS | 10 - Item shipped (return) | SMS | Lender | Return label first scan | Immediate | 📬 Sherbrt 🍧: "[Item]" is on its way back to you! Track the return here: [tracking_link].
11-SMS | 11 - Return delivered to lender | SMS | Lender | Return delivered scan | On first delivered scan (return) | 📦 Sherbrt 🍧: "[Item]" is back home! Thanks for sharing your style! 🫶🏽
Comms that must NOT fire (verify absence)
Log ID | Why it must NOT fire | [5 empty] | Absent? | Notes
1a-SMS | Lender accepted within 60m — nudge should not fire
1b-SMS | Lender accepted before 22h — final warning should not fire
2b-* | Lender did not decline
3.1* | Lender shipped before reminders trigger
3.2 / 3.2b | Booking shipped → no auto-cancel path
9.x | Borrower returned on time → no overdue path
SCENARIO 2 — IGNORED REQUEST (lender never accepts) [P0]
Goal | Confirm 60m + 22h escalation SMS fire, then 24h auto-expire (process.edn v5) cleanly without spurious downstream comms.
Setup | 1. Create IGNORED BORROWER + IGNORED LENDER. 2. Lender lists test item. 3. Borrower submits request. 4. Do NOT accept or decline. Wait 24+ hours. Tip: launch the request shortly before 8 AM PT so the 22h warning at the 22h mark also stays inside its window.
Related PR / Feature | 10.0 PR-4 (April 23 2026): process.edn v5 PT24H expire + 2-phase escalation in sendLenderRequestReminders.js + MISSED_FINAL watchdog.
How to observe | Twilio console (lender phone number, scenario tag), Render logs grep "[lender-request-reminder]", check no Sharetribe accept transition in Console.
Notes | 22h SMS bypasses quiet-hours by design — text may arrive at 2 AM if request was submitted at 4 AM. Expected.
Expected comms (should FIRE)
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Pass? | Notes
1-SMS | 1 - New borrow request | SMS | Lender | Request created | Immediate on submit | Sherbrt 🍧: ... You have 24hrs to accept: [request_link].
1-Email | 1 - New borrow request | Email | Lender | Request created | Immediate on submit | Sharetribe template booking-new-request
1a-SMS | 1a - 60m gentle nudge | SMS | Lender | 60m elapsed, no response | T+60min ([60m, 22h)) | Sherbrt 🍧: Don't leave [Borrower First Name] hanging! ... Just tap before it expires: [request_link].
1b-SMS | 1b - 22h final warning | SMS | Lender | 22h elapsed, no response | T+22h ([22h, 24h)) | Sherbrt 🍧: ⚠️ Final call — [Borrower First Name]'s request expires in 2 hours. ... |  | BYPASSES quiet-hours.
Sharetribe | 24h auto-expire email to borrower | Email | Borrower | transition/expire fires at 24h | 24h after request | Sharetribe template booking-expired-request — "Your booking request expired. Your card has not been charged."
Comms that must NOT fire (verify absence)
Log ID | Why it must NOT fire | [5 empty] | Absent? | Notes
2a / 2a-Email / 2c | No accept ⇒ no acceptance comms
2b / 2b-Email | No explicit decline ⇒ no decline comms
3 / 3.1 / 3.1b / 3.2 / 3.2b | No accept ⇒ no shipping or auto-cancel path
4 / 6 / 7 / 8 / 9.x / 10 / 11 | No accept ⇒ no downstream lifecycle
Duplicate 1a or 1b on same phase | Per-phase Redis dedupe should prevent double-sends
SCENARIO 3 — DECLINED REQUEST (lender explicitly declines) [P1]
Goal | Confirm lender decline fires 2b-SMS + 2b-Email to borrower, auto-releases the payment hold, no downstream comms fire. Promotes 2b-SMS / 2b-Email to Verified on pass.
Setup | 1. Create DECLINED BORROWER + DECLINED LENDER. 2. Lender lists test item. 3. Borrower submits request (lender receives 1-SMS + 1-Email). 4. Lender hits Decline in the Sherbrt UI within 60 minutes (so 1a/1b should not fire).
Related PR / Feature | 2b-SMS + 2b-Email — code location hypothesis: server/api/transition-privileged.js (decline branch). Not currently Verified.
How to observe | Twilio (borrower number for 2b-SMS), SendGrid (borrower email for 2b-Email), Stripe Dashboard (verify payment intent voided/uncaptured).
Notes | On pass, manually flip 2b-SMS + 2b-Email Verified column on Log tab to "Verified".
Expected comms (should FIRE)
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Pass? | Notes
1-SMS | 1 - New borrow request | SMS | Lender | Request created | Immediate | ...
1-Email | 1 - New borrow request | Email | Lender | Request created | Immediate | Sharetribe template
2b-SMS | 2b - Request rejected | SMS | Borrower | Lender declines | Immediate on decline transition | Sherbrt 🍧: Thanks for requesting "[Item]". This one wasn't available—browse more looks: [browse_link].
2b-Email | 2b - Request rejected | Email | Borrower | Lender declines | Immediate on decline transition | Sharetribe template booking-declined-request (or built-in fallback)
Comms that must NOT fire (verify absence)
Log ID | Why it must NOT fire | [5 empty] | Absent? | Notes
1a / 1b | Lender declined within 60m — neither escalation should fire
2a / 2a-Email / 2c | No accept ⇒ no acceptance comms
3 / 3.1 / 3.1b / 3.2 / 3.2b | No ship-by or auto-cancel path
4 / 6 / 7 / 8 / 9.x / 10 / 11 | No downstream lifecycle
SCENARIO 4 — UNSHIPPED (accepted but never shipped → auto-cancel) [P0]
Goal | End-to-end validation of auto-cancel: ship-by reminders fire, scan-lag grace observed, cancel transition fires after grace, full refund posts, Shippo labels void, both parties notified.
Setup | 1. Create UNSHIPPED BORROWER + UNSHIPPED LENDER. 2. Lender lists test item with a near-future bookingStart (e.g. tomorrow). 3. Borrower submits request. 4. Lender accepts. Shippo creates outbound label → 3-SMS. 5. DO NOT ship the item. 6. Wait through ship-by date. 7. Auto-cancel will fire ~noon D+1 lender-local (or D+2 for Monday-start) after 12h scan-lag grace.
Related PR / Feature | Step 3.2 auto-cancel-unshipped (Apr 14 2026, commit f17d91b18); B2 + B3 fixes (Apr 21, PR #53); 10.0 PR-5 scan-lag grace (Apr 23, PR #55); 3.2 / 3.2b copy update (Apr 28, in progress).
How to observe | Render logs filtered to [auto-cancel-unshipped] — look for SKIP reason=scan-lag-grace at first cron tick(s) past deadline, then transition fired at +12h. Stripe Dashboard for refund. Shippo Dashboard for voided labels. Sharetribe Console for protectedData.autoCancel.sent.
Notes | AUTO_CANCEL_DRY_RUN=0 is live in Render — this fires a real cancel + real refund. Use a low-priced test listing. Cron runs hourly on the hour.
Expected comms (should FIRE)
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Pass? | Notes
1-SMS | 1 - New borrow request | SMS | Lender | Request created | Immediate | ...
1-Email | 1 - New borrow request | Email | Lender | Request created | Immediate | Sharetribe template
2a-SMS | 2a - Request accepted | SMS | Borrower | Lender accepts | Immediate on accept | ...
2a-Email | 2a - Request accepted | Email | Borrower | Lender accepts | Immediate on accept | Sharetribe template
2c-SMS | 2c - Return Label Provided | SMS | Borrower | Lender accepts (same accept transition) | Immediate on accept | 📦 Your return label is ready! ...
3-SMS | 3 - Outbound label / QR created | SMS | Lender | Outbound label created | Immediate after accept | ...
3.1-SMS | 3.1 - Outbound ship reminder | SMS | Lender | T-24h to ship-by, no scan | T-24h | ⏰ Sherbrt 🍧 reminder: Please ship "[Item]" by tomorrow ...
3.1b-SMS | 3.1b - End-of-day unshipped | SMS | Lender | Ship-by day, EOD, no scan | Evening of [Ship-by Date] | Sherbrt 🍧: Heads up — "[Item]" still isn't scanned ...
3.2-SMS | 3.2 - Auto-cancel & refund | SMS | Borrower | bookingStart deadline + 12h scan-lag, no scan | ~noon D+1 lender-local | 🚫 Sherbrt 🍧: Your borrow request for "[Item]" was auto-canceled because the lender didn't ship in time. Full refund will hit your card in 5–10 business days. Browse other looks: [browse_link]
3.2b-SMS | 3.2 - Auto-expire notice | SMS | Lender | Same auto-cancel event as 3.2 | ~noon D+1 lender-local | ⚠️ Sherbrt 🍧: Your listing "[Item]" was auto-canceled because it wasn't shipped in time. You missed out on $[Lender Earnings]. Update your listing availability for future requests: https://sherbrt.com/listings
Observable: scan-lag-grace SKIP log (not an SMS)
Cron tick within 12h of cancel deadline | Render log: [auto-cancel-unshipped][txId] SKIP reason=scan-lag-grace hoursPastDeadline=X.X | [6 empty] | Confirms the grace guard fired at least once before the cancel.
Comms that must NOT fire (verify absence)
Log ID | Why it must NOT fire | [5 empty] | Absent? | Notes
2b / 2b-Email | Lender accepted, did not decline
4 / 6 | No outbound scan ⇒ no shipped/delivered comms
48h transition/cancel (legacy) | B3 deletion — the legacy 48h cancel block in sendShippingReminders is gone
Duplicate 3.2 / 3.2b | Idempotent via protectedData.autoCancel.sent — only one SMS pair per tx
SCENARIO 5 — LATE RETURN (borrower keeps past due → overdue + late-fee charges) [P0]
Goal | End-to-end validation of PR-4 staging dry-run: every day-N overdue SMS fires once, $0.50 test charges land on days 2–6, day-6 ops email + daily digest emails arrive, day 7+ hard stops.
Setup | 1. Create LATE BORROWER + LATE LENDER. 2. Lender lists item. 3. ENV PREREQUISITE in Render: set LATE_FEE_CENTS_OVERRIDE=50 AND OVERDUE_FEES_CHARGING_ENABLED=true on the Overdue cron. 4. Borrower submits request, lender accepts, lender ships, borrower receives. 5. Borrower DOES NOT ship return by [Return Date]. 6. Wait 7 days past return date. 7. After test, REVERT both env vars (set back to false / remove override).
Related PR / Feature | PR-4 staging dry-run (see PR-4 Instructions tab → renamed Late-Fee Charging Dry-Run). Validates 9.0 PR-1 to PR-5 in one shot.
How to observe | Twilio (borrower phone, days 1–6 SMS), Stripe Dashboard (5 × $0.50 captures on days 2–6), SendGrid (day-6 ops alert, daily digest each day), Sharetribe Console (return.chargeHistory and return.lastLateFeeDayCharged on tx protectedData), Render logs grep "overdue.charge".
Notes | 9.7-Email fires at end of every cron run with non-empty buckets — expect one per day during days 1–6. Quiet-hours gate (8 AM – 11 PM PT) applies to SMS; cron runs at 17:00 UTC = 10 AM PT, inside the window.
Expected comms (should FIRE)
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Pass? | Notes
1 through 8 | Full happy-path comms | Mixed | Both | Standard lifecycle through delivery | Per Scenario 1 | See Scenario 1 for full list
9.1-SMS | 9 - Overdue Day 1 (no charge) | SMS | Borrower | Day 1 cron run, no return scan | ~10 AM PT (17:00 UTC) | ⚠️ Your Sherbrt return for "[Item]" ended yesterday. $15/day late fee may apply ... |  | No charge — scan-lag-grace.
9.2-SMS | 9 - Overdue Day 2 ($15 charge #1) | SMS | Borrower | Day 2 cron, charge $0.50 for day 1 | ~10 AM PT | ⚠️ ... is now 2 days late. |  | Charge #1 of 5.
9.3-SMS | 9 - Overdue Day 3 ($15 charge #2) | SMS | Borrower | Day 3 cron, charge $0.50 for day 2 | ~10 AM PT | ⚠️ ... is now 3 days late. |  | Charge #2 of 5.
9.4-SMS | 9 - Overdue Day 4 ($15 charge #3) | SMS | Borrower | Day 4 cron, charge $0.50 for day 3 | ~10 AM PT | ⚠️ ... 4 days late. Replacement-value risk language. |  | Charge #3 of 5.
9.5-SMS | 9 - Overdue Day 5 ($15 charge #4) | SMS | Borrower | Day 5 cron, charge $0.50 for day 4 | ~10 AM PT | ⚠️ ... 5 days late. |  | Charge #4 of 5.
9.6-SMS | 9 - Overdue Day 6 ($15 charge #5, FINAL) | SMS | Borrower | Day 6 cron, charge $0.50 for day 5 | ~10 AM PT | 🚨 ... 6 days late. Replacement value may be charged. |  | Charge #5 of 5 = cap reached.
9.6-Email | 9 - Day 6 operator alert | Email | Operator (amalyb@gmail.com) | Day-6 SMS sent successfully | Immediately after Day 6 SMS | Subject: [Sherbrt] Day-6 overdue — manual replacement decision needed (tx ...)
9.7-Email | 9 - Daily late-fee digest | Email | Operator | End of cron run with charges | After cron completes | Subject: [Sherbrt] Late-fee digest [date] — $[total] ([N] charged) |  | Expect 1 per day, days 1–6.
10-SMS / 11-SMS | Return shipped + delivered | SMS | Lender | If borrower eventually ships return | Whenever return scan posts | Standard return-flow SMS |  | Optional — only if borrower ships before testing ends.
Comms that must NOT fire (verify absence)
Log ID | Why it must NOT fire | [5 empty] | Absent? | Notes
Duplicate 9.N on same day | Per-tx Redis dedupe overdueNotified:{txId}:{day}
9.x after return scan | Once carrier scan posts, overdue cron skips the tx
Day 7+ SMS or charge | Hard stop — count-based cap (5 × $15) reached
3.2 / 3.2b | Booking reached delivered → auto-cancel-unshipped path must not trigger
SCENARIO 6 — SUNDAY EDGE CASES (ship-by, return date, reminder day) [P2]
Goal | Cover the three Sunday-related fixes shipped April 14 2026. Each sub-case exercises a different code path; run independently.
Setup | Create SUNDAY BORROWER + SUNDAY LENDER. Run 3 sub-cases as separate bookings: A=ship-by Sunday → expect Saturday adjust; B=Sunday end-date banner on checkout (visual only); C=Saturday reminder fire for a Monday shipBy.
Related PR / Feature | Apr 14 2026 sunday handling commits + 10.0 PR-2 business-day-subtract helper (skips Sundays, includes Saturdays).
How to observe | Render logs grep "ship-by:adjust" or "ship-by:computed" or "ship-by:persisted"; checkout banner visual; Twilio for 3.1-SMS Saturday delivery.
Notes | No payment side-effects, low risk. Eligible to run anytime.
Expected comms (should FIRE)
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Pass? | Notes
Banner | Sub-case B: Sunday end-date notice | UI | Borrower (visual) | Sunday return at checkout | On checkout page | 'Sunday end date: Carriers don't run — ship Monday to avoid a late fee.'
3.1-SMS | Sub-case C: 24h reminder Saturday-fire | SMS | Lender | Saturday for Monday shipBy | T-24h, but anchored to Saturday since Sunday is non-business | 'Please ship by [Monday date]'. NO 'tomorrow' wording.
shipByDate adjust | Sub-case A: data-only | Data | (internal) | Sunday original shipBy | At label creation | protectedData.outbound.shipByDate lands on Saturday. Reason logged as sunday_to_saturday.
Comms that must NOT fire (verify absence)
Log ID | Why it must NOT fire | [5 empty] | Absent? | Notes
3.1-SMS on Sunday | Sub-case C: reminder must never fire on Sunday
Banner on listing page | Sub-case B: banner is checkout-only (showSundayEndDateNotice=false on listing page)
Late fee on Monday ship | Sub-case B: Monday ship after Sunday end date should be on-time (no 9.1, no charge)

## Log
Sherbrt — Transaction Communications Log
SMS & email touchpoints across the booking lifecycle. Dropdowns for Channel / Recipient / Verified. Filters live on the header row. See Legend tab for placeholder keys.
ID | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Message Example | Key Links | Verified | Policy / Notes | Coded | Code Location | Priority
1-SMS | 1 - New borrow request | SMS | Lender | Request created | Immediately when borrower submits request | Sherbrt 🍧: [Borrower First Name] wants to borrow your "[Item]", You'll earn [$Lender Earnings] 💸🤑. You have 24hrs to accept: [request_link]. | Sherbrt 🍧: Amalia wants to borrow your "Faille Halter Mini Dress". You'll earn $21.24 💸🤑. Tap to review & accept: https://sherbrt.com/sale/697a9426-9f99-4b5b-8894-f2b86b36c1c6 | Request / sale link | Verified | Start of transaction. Lender accept window = 24 hours via process.edn v5 (10.0 PR-4, April 23 2026) — was 6 days. After 24h, transition/expire fires automatically and the borrower is fully refunded. | Yes | server/api/initiate-privileged.js (tag: booking_request_to_lender_alt) | P1
1-Email | 1 - New borrow request | Email | Lender | Request created | Immediately when borrower submits request | Subject: [Borrower First Name] requested to book [Item] You have a new booking request for Faille Halter Mini Dress Amalia B requested to book Faille Halter Mini Dress in Sherbrt. Start End Sun Tue Feb 1 Feb 3 USD 8.33 × 3 days 24.99 USD Sherbrt fee -3.75 USD You'll earn 21.24 USD You need to accept the request by Feb 2, 2026, 12:00 AM. Otherwise the request will expire automatically and you won't get paid. If the booked dates don't work for you, you can also choose to decline the request. Accept or Decline the booking Can't click the button? Here's a link for your convenience: https://www.sherbrt.com/sale/697a9426-9f99-4b5b-8894-f2b86b36c1c6/ | Amalia B requested to book Faille Halter Mini Dress | Request / sale link; Help/FAQ link (optional) | Verified | Optional but recommended for lenders who don’t always see SMS. | Yes | Sharetribe built-in email template | P1
1a-SMS | 1a - 60m gentle nudge | SMS | Lender | Request reminder | 60min after initial request (phase 1 of 2) | Sherbrt 🍧: Don't leave [Borrower First Name] hanging! [$Lender Earnings] is waiting for you! 🤑🤑🤑 Just tap before it expires: [request_link]. | Sherbrt 🍧: Don't leave Amalia hanging! $51 is waiting for you! 🤑🤑🤑 Just tap to accept: https://sherbrt.com/sale/697a9426-9f99-4b5b-8894-f2b86b36c1c6 |  | Verified | Phase 1 of 2-phase escalation (10.0 PR-4). Respects 8 AM–11 PM PT quiet-hours (window is 21h wide so quiet-hours skip is absorbed). Per-phase Redis dedupe key lenderReminder:{txId}:60m:sent (TTL 7 days). | Yes | server/scripts/sendLenderRequestReminders.js (tag: lender_request_reminder_60m) | P1
1b-SMS | 1b - 22h final warning | SMS | Lender | 22h after request, 2h before auto-expire | [22h, 24h) — phase 2 of 2-phase escalation | Sherbrt 🍧: ⚠️ Final call — your [$Lender Earnings] payout is about to expire. Accept [Borrower First Name]'s borrow request now: [request_link] | Sherbrt 🍧: ⚠️ Final call — your $21.24 payout is about to expire. Accept Amalia's borrow request now: https://www.sherbrt.com/r/6MUUMC1920 | Request / sale link | Verified | BYPASSES 8 AM–11 PM PT quiet-hours by design — phase window is only 2h wide; quiet-hours skip would silently drop the warning. Per-phase Redis dedupe key lenderReminder:{txId}:22h:sent (TTL 7 days). MISSED_FINAL watchdog logs [MISSED_FINAL] tx=X if this fails to fire before auto-expire (steady-state count should be 0). | Yes | server/scripts/sendLenderRequestReminders.js (tag: lender_request_reminder_22h) | P0
1c-SMS | 1c - Borrower request expired | SMS | Borrower | transition/expire fires (24h auto-expire — lender never accepted) | Within 30 min of transition/expire (cron tick polls 15 min) | 😔 Sherbrt 🍧: Your borrow request was not accepted this time. Don't worry — there's still time to book another look you love! Check them out now! [browse_link] | 😔 Sherbrt 🍧: Your borrow request was not accepted this time. Don't worry — there's still time to book another look you love! Check them out now! https://www.sherbrt.com/r/lyBUNc13c1 | Browse/search link | Verified | Closes the loop for borrowers when the lender lets the 24h accept window run out (process.edn :transition/expire). Distinct from 2b-SMS (which fires on the lender clicking Decline). Piggybacks on the existing MISSED_FINAL watchdog query in sendLenderRequestReminders.js (lookback 30 min). Per-tx Redis dedupe key lenderReminder:{txId}:borrowerExpired:sent (TTL 7 days). DRY mode skips Redis writes. Tag: borrower_request_expired. | Yes | server/scripts/sendLenderRequestReminders.js (tag: borrower_request_expired) | P1
2a-SMS | 2a - Request accepted | SMS | Borrower | Lender accepts request | Immediately on accept transition | 🎉 Sherbrt 🍧: Your request for “[Item]” was accepted! We’ll share tracking once it ships. View details: [transaction_link]. | 🎉 Your Sherbrt request was accepted! 🍧 "Faille Halter Mini Dress" from Monica D is confirmed. You'll receive tracking info once it ships! ✈️👗 https://www.sherbrt.com/r/eKrfVC9aa1 | Transaction / order link | Verified | Depending on flow, card may now be charged or authorized. | Yes | server/api/transition-privileged.js (tag: accept_to_borrower + accept_to_lender) | P1
2a-Email | 2a - Request accepted | Email | Borrower | Lender accepts request | Immediately on accept transition | Subject: Your booking request was accepted Hi [Borrower First Name], Good news! Your request for “[Item]” was accepted by [Lender First Name]. You’ll receive tracking details once the item ships. View your booking here: [transaction_link]. By completing this booking, you agree to Sherbrt’s Terms, including late return and replacement policies: [terms_link]. Sip, slay, repeat ✨ Sherbrt 🍧 | Your booking request was accepted Monica D has accepted your booking request for Faille Halter Mini Dress from Feb 1, 2026 to Feb 3, 2026. Your card has been charged for USD 40.91. Here's the booking breakdown. Start End Sun Tue Feb 1 Feb 3 USD 8.33 × 3 days 24.99 USD Sherbrt fee 5.00 USD Total price 40.91 USD View order details Can't click the button? Here's a link for your convenience: https://www.sherbrt.com/order/697a9426-9f99-4b5b-8894-f2b86b36c1c6/ | Transaction / order link; Terms link | Verified | Reinforces terms at key commitment moment. | Yes | Sharetribe built-in email template | P1
2b-SMS | 2b - Request rejected | SMS | Borrower | Lender declines request | Immediately on decline transition | 😔 Sherbrt 🍧: Your borrow request was declined. Don't worry — new looks are waiting to be borrowed! Check them out! https://www.sherbrt.com/r/lyBUNc13c1 |  | Browse/search link |  | Flow ends for this transaction. | Yes | server/api/transition-privileged.js (tag: reject_to_borrower) | P2
2b-Email | 2b - Request rejected | Email | Borrower | Lender declines request | Immediately on decline transition | Subject: Update on your Sherbrt request Hi [Borrower First Name], Your request for “[Item]” wasn’t accepted this time. You’ve not been charged for this booking. Explore more outfits on Sherbrt here: [browse_link]. Sherbrt 🍧 |  | Browse/search link; Support link (optional) |  | Confirms no charge; nudges to keep browsing. | No | Not built — relies on Sharetribe default decline email | P2
2c-SMS | 2c- Return Label Provided | SMS | Borrower |  | Immediately on accept transition | 📦 Your return label is ready! Use this to ship back: [Label link] | 📦 Your return label is ready! Use this to ship back: https://www.sherbrt.com/r/M9PMIJ208f | Shipping label shippo link | Verified |  | Yes | server/api/transition-privileged.js (tag: return_label_ready_to_borrower) | P1
3-SMS | 3 - Outbound label / QR created | SMS | Lender | Outbound shipping label or QR created | When label creation succeeds | Sherbrt 🍧: Ship “[Item]” by [Ship-by Date]. Shipping label: [qr_or_label_link]. | Sherbrt : Ship "Faille Halter Mini Dress" by Apr 14. Shipping label: https://www.sherbrt.com/r/9W4qo8c4db | QR/label link; Tracking link (optional) | Verified | Ship-by anchored to the selected outbound Shippo rate estimated_days + SAFETY_BUFFER_DAYS (default 1), business-day-subtracted from bookingStart (skips Sundays + USPS holidays, includes Saturdays). Persisted at protectedData.outbound.shipByDate at label purchase (10.0 PR-2). All downstream consumers read this persisted value first. | Yes | server/api/transition-privileged.js (tag: label_ready_to_lender + label_created_to_borrower) | P0
3.1-SMS | 3.1 - Outbound ship reminder | SMS | Lender | 24 hours before ship-by date AND no carrier "accepted" scan yet | T-24h to [Ship-by Date] | ⏰ Sherbrt 🍧 reminder: Please ship “[Item]” by tomorrow, [Ship-by Date], so your borrower gets it on time. Use your QR/label: [qr_or_label_link]. |  | QR/label link |  | Reads persisted protectedData.outbound.shipByDate (10.0 PR-3) — no longer recomputes per cron with its own SHIP_LEAD_DAYS env var. Anchored to outbound.acceptedAt time-of-day, not UTC midnight. Only sends if still unshipped (no carrier "accepted" scan). | Yes | server/scripts/sendShippingReminders.js (tag: shipping_reminder_24h) | P0
3.1b-SMS | 3.1b - End-of-day unshipped reminder | SMS | Lender | Ship-by date AND no carrier "accepted" scan by end of ship-by day | Evening of [Ship-by Date] (after ~3pm PT / 6pm ET) | Sherbrt 🍧: Heads up — “[Item]” still isn't scanned for shipment on its ship-by day. Drop it with the carrier first thing tomorrow to avoid cancellation: [qr_or_label_link]. |  | QR/label link | Verified | Final nudge before the auto-cancel window opens. Reads persisted protectedData.outbound.shipByDate (10.0 PR-3). Tag: shipping_reminder_end_of_day. Redis idempotency key: shippingReminder:{txId}:eod:sent. | Yes | server/scripts/sendShippingReminders.js (tag: shipping_reminder_end_of_day) | P0
3.2-SMS | 3.2 - Auto-cancel & refund (unshipped) | SMS | Borrower | bookingStart deadline passed (11:59pm lender-local) + 12h scan-lag grace AND still no outbound "accepted" scan | ~noon D+1 lender-local for non-Monday bookings; ~noon D+2 for Monday-start (existing weekend grace shift) | 🚫 Sherbrt 🍧: Your borrow request for "[Item]" was auto-canceled because the lender didn't ship in time. Full refund will hit your card in 5–10 business days. Browse other looks: [browse_link] |  | Browse/search link; Support link (optional) |  | Auto-cancel anchored to bookingStart (NOT shipByDate). Cancel deadline = 11:59pm lender-local on bookingStart D, +12h scan-lag grace (10.0 PR-5). Effective cancel = 36h post-bookingStart for non-Monday, 60h for Monday-start. Cron tick within grace window logs SKIP reason=scan-lag-grace. transition/auto-cancel-unshipped fires full refund + voids Shippo labels. Idempotent via protectedData.autoCancel.sent. AUTO_CANCEL_DRY_RUN=0 (live mode). | Yes | server/scripts/sendAutoCancelUnshipped.js (tag: auto_cancel_to_borrower) | P0
3.2b-SMS | 3.2 - Auto-expire notice | SMS | Lender | Same auto-cancel event as 3.2-SMS | ~noon D+1 lender-local (or D+2 Monday-start), +12h scan-lag grace | ⚠️ Sherbrt 🍧: Your listing "[Item]" was auto-canceled because it wasn't shipped in time. You missed out on $[Lender Earnings]. Update your listing availability for future requests: https://sherbrt.com/listings |  | Dashboard / listings link (optional) |  | Earnings amount uses calculateLenderPayoutTotal helper (same source as 1-SMS / 1a-SMS / 1b-SMS) so the four lender-side messages can never drift on the figure shown. URL is the static ManageListingsPage (/listings route → user can update availability/edit listings). Replaces v4-era "Sherbrt here" + per-listing relist shortLink copy. | Yes | server/scripts/sendAutoCancelUnshipped.js (tag: auto_cancel_to_lender) | P0
4-SMS | 4 - Item shipped (outbound) | SMS | Borrower | Carrier scan status = accepted / in transit (outbound) | Immediately once first "accepted" scan is received | 🚚 Sherbrt 🍧: “[Item]” is on its way! Tracking info: [tracking_link]. |  | Tracking link |  | Direction must be outbound only. | Yes | server/webhooks/shippoTracking.js (tag: item_shipped_to_borrower) | P0
6-SMS | 6 - Item delivered to borrower | SMS | Borrower | Carrier status = delivered (outbound) | On first delivered scan | 🎁 Your Sherbrt borrow has arrived! 🎉 Slay & tag @shoponsherbrt 🍧 Need anything? bestie@sherbrt.com | 🎁 Your Sherbrt borrow has arrived! 🎉 Slay & tag @shoponsherbrt 🍧 Need anything? bestie@sherbrt.com | Transaction / order link (optional) | Verified | Confirms delivery + branding CTA. | Yes | server/webhooks/shippoTracking.js (tag: item_delivered_to_borrower) | P0
7-SMS | 7 - Borrower Return Reminder | SMS | Borrower | 1 day before [Return Date] AND no return accepted/in-transit scan yet | T-1 day to [Return Date] | 📦 Sherbrt 🍧: It's almost return time\! Use your QR/label to ship "[Item]" back tomorrow: [qr_or_label_link]. | 📦 Sherbrt 🍧: It's almost return time! Use your QR/label to ship "Faille Halter Mini Dress" back tomorrow: https://www.sherbrt.com/r/M9PMIJ208f. | Return QR/label link | In review | Interpolates ${itemTitle}; canonical lookup pd.returnQrUrl ¦¦ pd.returnLabelUrl, falling back to a Shippo re-fetch (resolveReturnLabelUrl via returnTransactionId) if both are missing; minted via shortLink() (21-day Redis TTL). Tag: return_tminus1_to_borrower. Fires while tx is in :state/accepted (borrower holds the item; :state/delivered only after the return scan). Fixed May 22 2026: the protectedData whitelist had been stripping returnQrUrl/returnLabelUrl, and the cron previously filtered :state/delivered with an off-by-one due date, so this never fired in prod. | Yes | server/scripts/sendReturnReminders.js (tag: return_tminus1_to_borrower) | P1
8-SMS | 8 - Day-of-return reminder | SMS | Borrower | [Return Date] AND no return accepted/in-transit scan | Morning of [Return Date] | ⏰ Sherbrt 🍧: Today's the day for you to ship back "[Item]"\! Late returns may incur $15/day fees. Use your QR/label to ship back: [qr_or_label_link]. | ⏰ Sherbrt 🍧: Today's the day for you to ship back "Faille Halter Mini Dress"\! Late returns may incur $15/day fees. Use your QR/label to ship back: https://www.sherbrt.com/r/M9PMIJ208f. | Return QR/label link; Terms link | In review | Fires in PT morning on [Return Date] = booking.end (PT calendar date). Same canonical label lookup + Shippo fallback and same :state/accepted gating as Step 7. Tag: return_reminder_today (with_label) or return_reminder_today_no_label fallback. Fixed May 22 2026 (see Step 7 notes). | Yes | server/scripts/sendReturnReminders.js (tags: return_reminder_today / return_reminder_today_no_label) | P1
9.1-SMS | 9 - Overdue Day 1 (SMS only, no charge) | SMS | Borrower | 1 chargeable day after [Return Date] AND no return scan. Cron: daily 17:00 UTC (~10 AM PT). | Day 1 cron run (no charge — scan-lag grace) | ⚠️ Your Sherbrt return for "[Item]" ended yesterday. $15/day late fee may apply until scanned by the carrier. Please ship today using your QR/label: [shortUrl]. For help: bestie@sherbrt.com. | ⚠️ Your Sherbrt return for "Faille Halter Mini Dress" ended yesterday. $15/day late fee may apply until scanned by the carrier. Please ship today using your QR/label: https://sherbrt.com/r/ABC123. For help: bestie@sherbrt.com. | Return QR/label short link | In review | Day 1 = SMS only, no charge (scan-lag-grace rule: charge for day N-1 on day N's cron, no day 0 to charge). Quiet-hours gate: 8 AM - 11 PM PT. Uses chargeable late days (excludes Sundays + USPS holidays). May 22 2026 fix: the return due date now resolves from the included booking resource (booking.end) - previously unresolved, so overdue SMS + charges never evaluated. Shares the Step 7/8 Shippo label fallback. | Yes | server/scripts/sendOverdueReminders.js → server/scripts/messages/overdueMessages.js (tag: overdue_day1_to_borrower) | P0
9.2-SMS | 9 - Overdue Day 2 ($15 charge #1) | SMS | Borrower | 2 chargeable days after [Return Date] AND no return scan. Cron: daily 17:00 UTC. | Day 2 cron run (charges $15 for day 1) | ⚠️ Your Sherbrt return for "[Item]" is now 2 days late. $15/day late fee applies until scanned by the carrier. Please ship today using your QR/label: [shortUrl]. | ⚠️ Your Sherbrt return for "Faille Halter Mini Dress" is now 2 days late. $15/day late fee applies until scanned by the carrier. Please ship today using your QR/label: https://sherbrt.com/r/ABC123. | Return QR/label short link | In review | Charge #1 of 5 ($15). Total to date: $15. Quiet-hours gate: 8 AM – 11 PM PT. | Yes | server/scripts/sendOverdueReminders.js → server/scripts/messages/overdueMessages.js (tag: overdue_day2_to_borrower) | P0
9.3-SMS | 9 - Overdue Day 3 ($15 charge #2) | SMS | Borrower | 3 chargeable days after [Return Date] AND no return scan. Cron: daily 17:00 UTC. | Day 3 cron run (charges $15 for day 2) | ⚠️ Your Sherbrt return for "[Item]" is now 3 days late. $15/day late fee applies until scanned by the carrier. Please ship today using your QR/label: [shortUrl]. | ⚠️ Your Sherbrt return for "Faille Halter Mini Dress" is now 3 days late. $15/day late fee applies until scanned by the carrier. Please ship today using your QR/label: https://sherbrt.com/r/ABC123. | Return QR/label short link | In review | Charge #2 of 5 ($30 total). Quiet-hours gate: 8 AM – 11 PM PT. | Yes | server/scripts/sendOverdueReminders.js → server/scripts/messages/overdueMessages.js (tag: overdue_day3_to_borrower) | P0
9.4-SMS | 9 - Overdue Day 4 ($15 charge #3) | SMS | Borrower | 4 chargeable days after [Return Date] AND no return scan. Cron: daily 17:00 UTC. | Day 4 cron run (charges $15 for day 3) | ⚠️ Your Sherbrt return for "[Item]" is now 4 days late. $15/day late fee continues and you may be charged the full replacement value. Ship immediately using your QR/label: [shortUrl]. For help: bestie@sherbrt.com. | ⚠️ Your Sherbrt return for "Faille Halter Mini Dress" is now 4 days late. $15/day late fee continues and you may be charged the full replacement value. Ship immediately using your QR/label: https://sherbrt.com/r/ABC123. For help: bestie@sherbrt.com. | Return QR/label short link | In review | Charge #3 of 5 ($45 total). Introduces replacement-value risk language. AUTO_REPLACEMENT_ENABLED = false — all replacements are manual/operator-only. | Yes | server/scripts/sendOverdueReminders.js → server/scripts/messages/overdueMessages.js (tag: overdue_day4_to_borrower) | P0
9.5-SMS | 9 - Overdue Day 5 ($15 charge #4) | SMS | Borrower | 5 chargeable days after [Return Date] AND no return scan. Cron: daily 17:00 UTC. | Day 5 cron run (charges $15 for day 4) | ⚠️ Your Sherbrt return for "[Item]" is now 5 days late. $15/day late fee continues. Ship immediately using your QR/label: [shortUrl] to avoid a replacement charge. For help: bestie@sherbrt.com. | ⚠️ Your Sherbrt return for "Faille Halter Mini Dress" is now 5 days late. $15/day late fee continues. Ship immediately using your QR/label: https://sherbrt.com/r/ABC123 to avoid a replacement charge. For help: bestie@sherbrt.com. | Return QR/label short link | In review | Charge #4 of 5 ($60 total). Final warning before Day 6 investigation. | Yes | server/scripts/sendOverdueReminders.js → server/scripts/messages/overdueMessages.js (tag: overdue_day5_to_borrower) | P0
9.6-SMS | 9 - Overdue Day 6 ($15 charge #5, FINAL + investigation) | SMS | Borrower | 6 chargeable days after [Return Date] AND no return scan. Cron: daily 17:00 UTC. | Day 6 cron run (charges $15 for day 5 — final late fee) | 🚨 Your Sherbrt return for "[Item]" is now 6 days late. Your borrow is being investigated and the full replacement value of the item may be charged. Please ship it back ASAP using your QR code or label: [shortUrl]. For help: bestie@sherbrt.com. | 🚨 Your Sherbrt return for "Faille Halter Mini Dress" is now 6 days late. Your borrow is being investigated and the full replacement value of the item may be charged. Please ship it back ASAP using your QR code or label: https://sherbrt.com/r/ABC123. For help: bestie@sherbrt.com. | Return QR/label short link | In review | Charge #5 of 5 ($75 total, MAX cap reached). Day 7+ = hard stop (no SMS, no charge). Triggers day-6 operator email alert (see 9.6-Email). Replacement is manual/operator-only. | Yes | server/scripts/sendOverdueReminders.js → server/scripts/messages/overdueMessages.js (tag: overdue_day6_to_borrower) | P0
9.6-Email | 9 - Overdue Day 6 operator email alert | Email | Operator | Day-6 SMS sent successfully (smsResult not skipped) | Immediately after Day 6 SMS fires (fire-and-forget) | Subject: [Sherbrt] Day-6 overdue — manual replacement decision needed (tx [txId]) Day-6 SMS just fired to borrower — replacement charge commitment is now in effect. Tx: [txId] Listing: [listingTitle] ([listingId]) Borrower: [customerName] ([borrowerPhone]) Return due: [returnDate] Days late: 6 Action: decide whether to trigger manual replacement charge. Console: https://console.sharetribe.com/o/sherbrt/transactions/[txId] | Subject: [Sherbrt] Day-6 overdue — manual replacement decision needed (tx 693c9fee) Day-6 SMS just fired to borrower... | Sharetribe Console tx link | Verified | Fire-and-forget with .catch() — SendGrid failure logged but does not crash cron. DRY_RUN respected. Rides SMS Redis dedupe (no separate email key). Recipient: OPS_ALERT_EMAIL env var (defaults amalyb@gmail.com). | Yes | server/scripts/sendOverdueReminders.js (uses server/email/emailClient.js sendTransactionalEmail) | P0
9.7-Email | 9 - Daily late-fee digest | Email | Operator | End of overdue cron run (chargeDigest.length > 0) | After all txs processed in daily cron run | Subject: [Sherbrt] Late-fee digest [date] — $[total] ([N] charged) Sherbrt late-fee digest for [date] Charged: $[total] across [N] tx(s) tx [txId] — "[listingTitle]" ([borrowerName]) — day [N] — $[amount] Skipped: [N] Flag: LIVE / DISABLED | Subject: [Sherbrt] Late-fee digest 2026-04-16 — $15.00 (1 charged) Charged: $15.00 across 1 tx(s)... | None | Verified | In-cron accumulation (Model B: charged + skipped_* buckets only). Gated by \!DRY_RUN. Empty days = no email (silence is fine). Recipient: OPS_ALERT_EMAIL env var (defaults amalyb@gmail.com). | Yes | server/scripts/sendOverdueReminders.js sendLateFeeDigest() helper (uses server/email/emailClient.js) | P1
10-SMS | 10 - Item shipped (return) | SMS | Lender | Return label status = accepted / in transit | Immediately once carrier return scan is accepted | 📬 Sherbrt 🍧: "[Item]" is on its way back to you\! Track the return here: [tracking_link]. | 📬 Sherbrt 🍧: "Faille Halter Mini Dress" is on its way back to you\! Track the return here: https://www.sherbrt.com/r/9W4qo8c4db. | Return tracking link | Verified | Interpolates listingTitle from shippoTracking included map. Fires on first return carrier scan (direction=return). Idempotent via protectedData.return.firstScanAt. | Yes | server/webhooks/shippoTracking.js (tag: return_first_scan_to_lender) | P0
11-SMS | 11 - Return delivered to lender | SMS | Lender | Return label carrier status = delivered | On first delivered scan (direction=return) | 📦 Sherbrt 🍧: "[Item]" is back home\! Thanks for sharing your style\! 🫶🏽 Just in case: bestie@sherbrt.com 💌 | 📦 Sherbrt 🍧: "Faille Halter Mini Dress" is back home\! Thanks for sharing your style\! 🫶🏽 Just in case: bestie@sherbrt.com 💌 | None (confirmation only) | Verified | NEW (April 15, 2026). Idempotent via protectedData.return.deliveredNotificationSentAt. Also writes protectedData.return.deliveredAt. Tag: SMS_TAGS.RETURN_DELIVERED_TO_LENDER. Closes the loop for lenders after return delivery. | Yes | server/webhooks/shippoTracking.js (tag: return_delivered_to_lender) | P0

## Legend
Legend & Conventions
Channel | SMS · Email · SMS+Email. Dropdown on the Comms Log. Color chip applied automatically.
Recipient | Lender · Borrower · Both. Dropdown. Color chip applied automatically.
Verified | Verified · In review · Broken · Not yet live. Dropdown with color chip. Leave blank if not yet QA'd.
Placeholders | [Borrower First Name], [Item], [$Lender Earnings], [request_link], [qr_or_label_link], [tracking_link], [terms_link], [transaction_link], [browse_link], [support_link], [Ship-by Date], [Return Date], [Replacement Value].
Ship-by logic | Ship-by is anchored to the selected outbound Shippo rate's estimated_days + SAFETY_BUFFER_DAYS (default 1), business-day-subtracted from bookingStart. Business-day rule skips Sundays + USPS holidays, INCLUDES Saturdays. Persisted at protectedData.outbound.shipByDate at label purchase; all downstream crons read the persisted value first. Static SHIP_LEAD_DAYS env var is fallback-only when Shippo data unavailable.
Late fees | $15 / day starting +24h after return date, excluding Sundays & USPS holidays. Replacement charge at Day 5.
ID convention | Numbered by lifecycle step. Suffix -SMS or -Email indicates channel. Sub-steps use letters (e.g. 2a, 3.2, 9.3).
Google Sheets | Opens directly in Sheets (File → Open → Upload). Dropdowns, filters, conditional formatting, and summary formulas are all preserved on upload.
Quiet Hours | All SMS daemons gated by withinSendWindow(): 8 AM – 11 PM PT. Outside this window, messages are deferred to the next poll cycle (Pattern A) or next morning (Pattern B for lender request reminders). See server/util/time.js.
Late Fee Cap | Max 5 charges × $15 = $75 total. Count-based (chargeHistory entries with code="late-fee"), not day-based. Day 7+ = hard stop (no SMS, no charge).
Lender accept window | 24 hours from request submission (process.edn v5, 10.0 PR-4). Two-phase SMS escalation: 60m gentle nudge respects 8 AM–11 PM PT quiet-hours; 22h final warning bypasses quiet-hours by design (phase window is only 2h, can't afford a quiet-hours skip). Auto-expires at 24h with full borrower refund via transition/expire.
Auto-cancel scan-lag grace | 12-hour buffer past the cancel deadline (11:59pm lender-local on bookingStart D) before sendAutoCancelUnshipped fires (10.0 PR-5). Avoids premature cancels when carriers — especially USPS, 4–12h scan lag — haven't yet propagated the scan. Effective cancel window: 36h post-bookingStart for non-Monday, 60h for Monday-start.

## Future Comms
Sherbrt — Future Comms (Backlog)
Parked messaging ideas and partially-built touchpoints. Move items to the Log tab when promoted to live. Priority: P0 = this sprint, P1 = next, P2 = nice-to-have.
Priority | Flow Step | Channel | Recipient | Event / Trigger | Timing | Message Copy | Dependencies | Status | Rationale / Notes
P2 | 4 - Item shipped (outbound) email | Email | Borrower | Outbound carrier status = accepted / in_transit | Immediately on first accepted scan | Subject: Your Sherbrt item is on the way! 🚚 Hi [Borrower First Name], Your "[Item]" has shipped! Track it here: [tracking_link]. Enjoy it until [Return Date] — late fees apply after that date. Terms: [terms_link]. Sherbrt 🍧 | SendGrid template | Not started | SMS covers the urgent notice. Email is nice-to-have for record/receipt. Check whether Sharetribe already sends a native notification before building.
P2 | 6 - Item delivered email | Email | Borrower | Outbound carrier status = delivered | On first delivered scan | Subject: Your Sherbrt item has arrived ✨ Hi [Borrower First Name], Your "[Item]" has been delivered. Enjoy it until [Return Date]. On return day, use your QR/label to ship it back. Late returns may incur $15/day fees and, if not returned in good condition, a replacement charge up to the item's replacement value. See Terms: [terms_link]. Don't forget to tag @shoponsherbrt on Instagram 📸✨ Sherbrt 🍧 | SendGrid template | Not started | Marketing-driven: Instagram CTA + terms recap. Build after P0/P1 items land.
P1 | 2b - Prepping your borrow (new) | SMS | Borrower | Lender label printed / 12h after accept with no ship scan | T+12h from accept transition OR on label print event | Sherbrt 🍧: “[Item]” is being prepped for you ✨ We'll text tracking the moment it ships. View details: [transaction_link]. | Twilio + label-print webhook OR cron check | Proposed | Closes the silence between accept (2a-SMS) and outbound shipped (4-SMS), which can be 24–48h apart. Sets expectations and reduces "did my lender forget" anxiety.

## Late-Fee Charging Dry-Run
PR-4 — Staging Dry-Run Instructions
Verify the late-fee charging pipeline end-to-end with $0.50 test charges before flipping to $15.
Environment Variables (Render Dashboard)
# | Variable | Value | Purpose
1 | OVERDUE_FEES_CHARGING_ENABLED | true | Enables the Stripe transition call in applyCharges(). Default: false.
2 | LATE_FEE_CENTS_OVERRIDE | 50 | Overrides LATE_FEE_CENTS from 1500 ($15) to 50 ($0.50). Remove after test.
3 | OPS_ALERT_EMAIL | amalyb@gmail.com | Recipient for day-6 alert + daily digest emails. Already set if using default.
Step-by-Step
Step | Action | How to Verify | Notes
1 | Set env vars in Render dashboard | Render → Environment → add/edit the 2 vars above → Save → auto-deploy triggers | No code change needed. Deploy takes ~2-3 min.
2 | Create a test transaction | Create a borrow request with a return date in the past (or use FORCE_TODAY to simulate). The tx must be in "accepted" state with no return scan. | Tip: set return due date to yesterday so Day 1 triggers on next cron run.
3 | Wait for cron or trigger manually | Run: node server/scripts/sendOverdueReminders.js --verbose Or wait for 17:00 UTC automatic run. | Manual run uses the same code path as the cron. Use FORCE_NOW/FORCE_TODAY for date simulation.
4 | Check Render logs for structured events | Search for: "overdue.charge" Expect: {"event":"overdue.charge","txId":"...","amounts":[{"code":"late-fee","cents":50}]} No "overdue.charge.error" events. | The structured JSON logs (PR-5) are filterable by event field.
5 | Verify in Stripe | Find the payment intent for the test tx. Should show a $0.50 capture (not $15). | Stripe Dashboard → Payments → search by tx ID or amount.
6 | Verify in Sharetribe Console | Check tx protectedData → return.chargeHistory has new entry with amount: 50. Check return.lastLateFeeDayCharged is set to today's date. | Console: https://console.sharetribe.com/o/sherbrt/transactions/[txId]
7 | Verify day-6 email (if testing day 6) | Check amalyb@gmail.com for "[Sherbrt] Day-6 overdue" email. Check for daily digest email after cron completes. | Day-6 email only fires when daysLate === 6 AND SMS succeeds.
8 | REVERT env vars in Render | Set OVERDUE_FEES_CHARGING_ENABLED = false Remove LATE_FEE_CENTS_OVERRIDE Save → auto-deploy | CRITICAL: Do not leave charging enabled at $0.50 in prod.
⚠️ | AFTER TESTING: Proceed to PR-6 | Once verified, set OVERDUE_FEES_CHARGING_ENABLED=true and REMOVE LATE_FEE_CENTS_OVERRIDE to charge $15. This is PR-6 (the flag flip). | Do NOT set both at once — remove the override first, then enable.

## Inbox Comms
Sherbrt — Inbox Page Titles (default-booking)
User-facing titles rendered on the Inbox + TransactionPage views. Backend "activity" = Sharetribe state (post-transition state name). Sourced from src/translations/en.json (TransactionPage.default-booking.* keys). Mobile mirror: lib/transactions.ts STATE_TO_STATUS / STATE_TO_LENDER_STATUS.
Recipient | Backend State (Sharetribe) | Triggering Transition | Inbox Title (User Sees) | en.json Key | Mobile Label (lib/transactions.ts) | Notes
Borrower | inquiry | transition/inquire | You sent an inquiry. | TransactionPage.default-booking.customer.inquiry.title | Inquiry sent | Optional inquiry path.
Borrower | pending-payment | transition/request-payment | {customerName}, you haven't confirmed the payment yet. | TransactionPage.default-booking.customer.pending-payment.title | Finishing payment… | Borrower at Stripe checkout. 15-min window.
Borrower | payment-expired | transition/expire-payment | Request expired. | TransactionPage.default-booking.customer.payment-expired.title | Payment didn't go through (mobile) | May 7, 2026 copy refresh — was "You didn't confirm the payment in time." (borrower-blamey). 15-min Stripe checkout timeout. Mobile label still says "Payment didn't go through" — pending mobile sync.
Borrower | preauthorized | transition/confirm-payment | Your booking request was successful! | TransactionPage.default-booking.customer.preauthorized.title | Waiting for lender | Awaiting lender accept (24h window).
Borrower | preauthorized (extra) | transition/confirm-payment | You'll be notified when {providerName} accepts your request. | TransactionPage.default-booking.customer.preauthorized.extraInfo | — | Sub-title under the preauthorized state.
Borrower | expired | transition/expire | Your booking request expired. | TransactionPage.default-booking.customer.expired.title | Request expired | Lender did not accept in 24h. Triggers the new 1c-SMS (Log tab).
Borrower | declined | transition/decline / operator-decline | Your booking request was declined. | TransactionPage.default-booking.customer.declined.title | Lender declined | Lender clicked Decline. Triggers 2b-SMS (Log tab).
Borrower | accepted | transition/accept / operator-accept | Your booking request was accepted! | TransactionPage.default-booking.customer.accepted.title | In progress | Triggers 2a-SMS / 2a-Email + Shippo label flow.
Borrower | canceled | transition/cancel / auto-cancel-unshipped | Your booking was canceled. | TransactionPage.default-booking.customer.canceled.title | Canceled | Operator cancel or 3.2-SMS auto-cancel-unshipped.
Borrower | delivered | transition/complete-return / complete-replacement / operator-complete | Your booking was completed. | TransactionPage.default-booking.customer.delivered.title | Returned | Return scan or operator close-out.
Borrower | reviewed-by-customer | transition/review-1-by-customer | Your booking was completed. | TransactionPage.default-booking.customer.reviewed-by-customer.title | Awaiting lender review | Same title as delivered — diff is in the activity feed.
Borrower | reviewed-by-provider | transition/review-1-by-provider | Your booking was completed. | TransactionPage.default-booking.customer.reviewed-by-provider.title | Awaiting your review | Reviewing reciprocally; lender reviewed first.
Borrower | reviewed | transition/review-2-by-* / expire-review-period | Your booking was completed. | TransactionPage.default-booking.customer.reviewed.title | Complete | Both reviews published or 7d expiry.
Borrower | initial | — | Booking initiated. | TransactionPage.default-booking.customer.initial.title | — | Pre-request placeholder; rarely visible in inbox.
Lender | inquiry | transition/inquire | You received an inquiry from {customerName}. | TransactionPage.default-booking.provider.inquiry.title | Customer inquiry | Optional inquiry path.
Lender | pending-payment | transition/request-payment | Payment hasn't been confirmed yet. | TransactionPage.default-booking.provider.pending-payment.title | Awaiting payment | Borrower still at Stripe checkout.
Lender | payment-expired | transition/expire-payment | Request not accepted. | TransactionPage.default-booking.provider.payment-expired.title | Payment didn't go through (mobile) | May 7, 2026 copy refresh — was "Payment wasn't confirmed in time." (confusing for lender). Mobile label pending sync.
Lender | preauthorized | transition/confirm-payment | You received a booking request from {customerName}. | TransactionPage.default-booking.provider.preauthorized.title | New request | Lender Action: accept or decline within 24h. Triggers 1-SMS / 1a-SMS (60m) / 1b-SMS (22h).
Lender | expired | transition/expire | The request from {customerName} expired. | TransactionPage.default-booking.provider.expired.title | Request expired (no response) | Lender did not accept in 24h. Borrower receives 1c-SMS at this transition.
Lender | declined | transition/decline / operator-decline | The request from {customerName} was declined. | TransactionPage.default-booking.provider.declined.title | You declined | Lender clicked Decline.
Lender | accepted | transition/accept / operator-accept | You accepted a booking request from {customerName}. | TransactionPage.default-booking.provider.accepted.title | In progress | Lender clicked Accept; Shippo label flow starts.
Lender | canceled | transition/cancel / auto-cancel-unshipped | The booking from {customerName} was canceled. | TransactionPage.default-booking.provider.canceled.title | Canceled | Operator cancel or auto-cancel-unshipped.
Lender | delivered | transition/complete-return / complete-replacement / operator-complete | The booking from {customerName} was completed. | TransactionPage.default-booking.provider.delivered.title | Returned | Return scan or operator close-out.
Lender | reviewed-by-customer | transition/review-1-by-customer | The booking was completed. | TransactionPage.default-booking.provider.reviewed-by-customer.title | Awaiting your review
Lender | reviewed-by-provider | transition/review-1-by-provider | The booking was completed. | TransactionPage.default-booking.provider.reviewed-by-provider.title | Awaiting customer review
Lender | reviewed | transition/review-2-by-* / expire-review-period | The booking from {customerName} was completed. | TransactionPage.default-booking.provider.reviewed.title | Complete